## clinton
Clinton Proposed CSC Actions
PE Section Number | Action | Min Points | Max Points | Requested Points | Est Completion | Primaries
Required
1.2 (PE1) | Taskforce creation and minutes of 2 meetings | 20 | 20 | 20 | 5/20/2020 (Updated Jan 2024) | Steve and Carol | Docs uploaded to CSC Portal
1.3 (PE1) | Appoint Taskforce Coordinator | 10 | 10 | 10 | 5/20/2020 (Updated Jan 2024) | Steve and Carol | Docs uploaded to CSC Portal
Priority
2.1 (PE 2) | Develop government oprations GHG emissions inventory | 16 | 16 | 16 | 2022-03-31 | Steve B and Aaron | completed and uploaded to CSC
7.1 (PE 7) | Conduct Vulnerability Assessment | 4 | 16 | 16 | 2022-12-31 | Aaron and students | Completed and report uploaded to CSC
9.1 (PE 9) | Climate Change Education and Engagement | 4 | 8 | 8 | 2022-06-30 | Alma | Completed; plan submitted with supporting documents to CSC
2.6 (PE 2) | Develop Community Climate Action Plan | [16] | [16] |  | 2023-06-30 | Alma, Aaron | Planned; Village has created template
6.9 (PE6) | Adopt Complete Streets Policy- Priority Action | 4 | 4 | 4 | 2021-05-31 | Kathy and Steve | Resolution passed, no additional word done (may need plan on how to achieve for CSC points)
Others
3.32 (PE 3) | Conduct energy benchmarking for govt bldgs | 2 | 4 | 4 | 2020-07-19 | Steve B and Aaron | CEC action, docs uploaded. Village should report annually on its website for 4 pts.
3.15 (PE 3) | Install LED streetlights | 4 | 12 | 4 | 2020-07-19 | Steve B | CEC action, docs uploaded
PE 3 | Outdoor lighting reduction | 1 | 4 | 3 | 2020-07-19 | ? | Completed and docs uploaded
3 (PE 3) | Energy Code Enforcement Training | 5 | 5 | 5 | 2020-07-19 | Steve B | CEC actions, docs uploaded
6.3 (PE 6) | Adopt Unified Solar Permit | 5 | 5 | 5 | 2020-07-19 | Steve B | CEC actions, docs uploaded
3.2 (PE3) | Interior Lighting Upgrades | 1 | 5 | 2 | 2020-08-20 | Steve B | Docs uploaded to CSC Portal
10.3 (PE 1) | Partnership with other entities | 3 | 3 | 3 | 2021-01-31 | Carol | completed and info uploaded to CSC
1.5 (PE 1) | National/Regional Climate Program | 3 | 3 | 3 | 2021-01-31 | Carol | completed and info uploaded to CSC
8 (PE8) | Community Campaign (Heatsmart Clean Heating) | 3 | 3 | 3 | 2022-04-27 | Steve O | completed and info uploaded to CSC
9 (PE 9) | Climate related Public Event (Tabling at the Farmers Market) | 3 | 9 | 3 | 2024-01-31 | Sally | Completed and uploaded; amended to Farmers Market (timing requirements)
8 (PE8) | Farmers Market | 3 | 3 | 3 | 2022-07-01 | Carol G | completed and info uploaded to CSC
PE 3 | Fleet Inventory | 4 | 4 | 4 | 2023-12-11 | Steve O | Completed and info uploaded to CSC
PE 6 | Local Forestry Program | 1 | 10 | 8 | 2023-12-11 | ? | Completed and info uploaded to CSC (tree inventory, ordinance and mgmt plan)
9.4(PE 9) | Develop and maintain website on CSC | 3 | 3 | 3 | 9/20/2020 (Updated Jan 2024) | Alan & Alma | Completed and info uploaded to CSC
5.11 (PE 5) | Residential Organic Waste Program (Yard Waste Collection Program) | 2 | 16 | 10 | 2021-10-21 | Liseli & Mona | completed and info uploaded to CSC
9.4 (PE 9) | Social Media to inform public about progress | [3] | [3] |  | 2021-12-31 | Alan & Alma | Planned (not submitted as completed)
10.1 | Report Progress Annually | 4 | 4 |  | 2021-12-31 | All | progress rpt generally describes progress on climate action plan or other action oriented plan on climate initiative
6.1 | Develop Comprehensive plan with sustainability elements | [3] | [21] |  |  | Steve B and Joanne | Village applied for grant to fund
PE 7 | Cooling Centers | [1] | [9] |  |  | Liseli | Planning to create cooling center in Village
PE 9 | Energy Reduction Campaign | [5] | [5] | [5] |  |  | Focused on Heat Smart campaign
| Total | 105 | 167 | 137
Other Actions to Consider
7.15 | Natl Flood Insur Prog Comm Rating System | 3 | 9 |  |  | Aaron | May discuss at Meeting on Flooding
| Total with additional considered actions | 108 | 176
Note: 3 Priority Actions and 120 points required to achieve bronze
2022-08-09

## kirkland
Kirkland Proposed CSC Actions
PE Section Number | Action | Min Points | Max Points | Requested Points | Est Completion | Primaries
Required
1.2 (PE 1) | Taskforce creation and minutes of 2 meetings | 20 | 20 | 20 | 2020-05-20 | Carol and Garry | Docs uploaded to CSC Portal
1.3 (PE 1) | Appoint Taskforce Coordinator | 10 | 10 | 10 | 2020-05-20 | Carol and Garry | Docs uploaded to CSC Portal
Priority
2.1 (PE 2) | Develop government oprations GHG emissions inventory | [16] | [16] |  | 2022-02-21 | Gary and Aaron | Planned; Hamilton students assist
7.1 (PE 7) | Conduct Vulnerability Assessment | 4 | 16 | 16 | 2021-12-31 | Aaron | report being finalized
9.1 (PE 9) | Climate Change Education and Engagement | 4 | 8 | 8 | 2022-06-30 | Alma | Alma Prepared Initial Draft, Subcommittee to work on
2.6 (PE 2) | Develop Community Climate Action Plan | [16] | [16] |  | 2023-06-30 | Alma and Aaron | Planned, but not begun
6.9 (PE 6) | Adopt Complete Streets Policy- Priority Action | 4 | 4 | 4 | 2021-05-21 | Kathy and Steve | Resolution passed, but need plan on how to achieve for CSC points
Others
3.32 (PE 3) | Complete energy benchmarking for govt bldgs | 2 | 4 | 2 | 2021-01-31 | Gary & Aaron | CEC action, docs uploaded. Town should publish annually on website for 4 points.
3.15 (PE 3) | Install LED streetlights | 4 | 12 | 4 | 2020-07-19 | Garry | CEC action, docs uploaded
3 (PE 3) | Energy Code Enforcement Training | 5 | 5 | 5 | 2020-07-19 | Gary | CEC action, docs uploaded
6.3 (PE 6) | Adopt Unified Solar Permit | 5 | 5 | 5 | 2020-07-19 | Gary | CEC action, docs uploaded
3.2 (PE 3) | Interior Lighting Upgrades | 1 | 5 | 5 | 2021-01-31 | Gary & Carol | completed and docs uploaded to CSC
10.3 (PE 1) | Partership with Other Entities | 3 | 3 | 3 | 2021-01-31 | Carol | completed and info uploaded to CSC
1.5 (PE 1) | National/Regional Climate Program | 3 | 3 | 3 | 2021-01-31 | Carol | completed and info uploaded to CSC
9.4 (PE 9) | Develop and maintain website on CSC | 3 | 3 |  | 2020-09-20 | Alan & Alma | completed and info uploaded to CSC
8 (PE 8) | Community Campaign (Heatsmart Clean Heating) | 3 | 3 | 3 | 2022-04-27 | Steve O | completed and info uploaded to CSC
9 (PE 9) | Climate related Public Event (EV at Car Show) | 3 | 3 | 3 | 2022-06-13 | Sally C | completed and info uploaded to CSC (May need to rely on more recent event)
PE 7 | Cooling Centers | [1] | [9] |  |  |  | Planned
5.11 (PE 5) | Residential Organic Waste Program (Yard Waste Collection Program) | 2 | 22 | 6 | 2021-11-21 | Liseli & Mona | completed and info uploaded to CSC
9.4 (PE 9) | Social Media to inform public about progress | 3 | 3 |  | 2021-12-31 | Alan & Alma | Planned
10.1 | Report Progress Annually | 4 | 4 |  | 2021-12-31 | All | progress rpt generally describes progress on climate action plan or other action oriented plan on climate initiative
PE 3 | Government Building Energy Audit | [8] | [8] |  |  |  | Planned
PE 3 | Fleet Inventory | [4] | [4] |  |  |  | Planned
PE 7 | Watershed Plan for Water Quallity | [2] | [6] |  |  |  | Planned
PE 9 | Energy Reduction Campaign | 5 | 5 |  | 2024-05-23 |  | Heat Smart Campaign (need NYSERDA certification of completion)
| Total | 88 | 138
Other Actions to Consider
| Natl Flood Insur Prog Comm Rating System | 3 | 9 |  |  | Aaron and Steve | May discuss at Meeting on Flooding
7.15
| Total with additional considered actions | 91 | 147
Note: 3 Prioirity Actions and 120 points required to achieve bronze
2022-08-09