## clinton
Clinton Proposed CSC Actions
PE Section Number | Action | Min Points | Max Points | Est Completion | Primaries
Required
1.2 | Taskforce creation and minutes of 2 meetings | 20 | 20 | 2020-05-20 | Steve and Carol | Docs uploaded to CSC Portal
1.3 | Appoint Taskforce Coordinator | 10 | 10 | 2020-05-20 | Steve and Carol | Docs uploaded to CSC Portal
Priority
2.1 | Develop government oprations GHG emissions inventory | 16 | 16 | 2022-03-31 | Steve B and Aaron | completed and uploaded to CSC
7.1 | Conduct Vulnerability Assessment | 4 | 16 | 2021-12-31 | Aaron and students | report being finalized
9.1 | Climate Change Education and Engagement | 4 | 8 | 2022-06-30 | Alma | Alma Prepared Initial Draft, subcommittee to work on
2.6 | Develop Community Climate Action Plan | 16 | 16 | 2023-06-30 | Alma, Aaron | to begin spring, 2022 with assistance and input from Ham students and community?
Others
3.32 | Conduct energy benchmarking for govt bldgs | 2 | 4 | 2020-07-19 | Steve B and Aaron | CEC action, docs uploaded. Village should report annually on its website for 4 pts.
3.15 | Install LED streetlights | 5 | 10 | 2020-07-19 | Steve B | CEC action, docs uploaded
3 | Energy Code Enforcemet Training | 5 | 5 | 2020-07-19 | Steve B | CEC actions, docs uploaded
6.3 | Adopt Unified Solar Permit | 5 | 5 | 2020-07-19 | Steve B | CEC actions, docs uploaded
3.2 | Interior Lighting Upgrades | 1 | 5 | 2020-08-20 | Steve B | Docs uploaded to CSC Portal
10.3 | Partnership with other entities | 3 | 3 | 2021-01-31 | Carol | completed and info uploaded to CSC
1.5 | National/Regional Climate Program | 3 | 3 | 2021-01-31 | Carol | completed and info uploaded to CSC
8 | Community Campaign (Heatsmart Clean Heating) | 3 | 3 | 2022-04-27 | Steve O | completed and info uploaded to CSC
9 | Climate related Public Event (EV at Car Show) | 3 | 3 | 2022-06-13 | Sally C | completed and info uploaded to CSC
8 | Farmers Mket | 3 | 3 | 2022-07-01 | Carol G | completed and info uploaded to CSC
6.9 | Adopt Complete Streets Policy- Priority Action | 0 | 0 | 2021-05-31 | Kathy and Steve | Resolution passed, but need plan on how to achieve for CSC points
9.4 | Develop and maintain website on CSC | 3 | 3 | 2020-09-20 | Alan & Alma | Clinton needs to add link on Clim Change which provides info and link to CSC Taskforce
5.11 | Yard Waste Collection Program | 2 | 22 | 2021-10-21 | Liseli & Mona | completed and info uploaded to CSC
9.4 | Social Media to inform public about progress | 3 | 3 | 2021-12-31 | Alan & Alma
10.1 | Report Progress Annually | 4 | 4 | 2021-12-31 | All | progress rpt generally describes progress on climate action plan or other action oriented plan on climate initiative
6.1 | Develop Comprehensive plan with sustainability elements | 3 | 3 |  | Steve B and Joanne | Village applied for grant to fund
| Total | 118 | 165
Other Actions to Consider
7.15 | Natl Flood Insur Prog Comm Rating System | 3 | 9 |  | Aaron | May discuss at Meeting on Flooding
| Total with additional considered actions | 121 | 174
Note: 3 Priority Actions and 120 points required to achieve bronze
2022-08-09

## kirkland
Kirkland Proposed CSC Actions
PE Section Number | Action | Min Points | Max Points | Est Completion | Primaries
Required
1.2 | Taskforce creation and minutes of 2 meetings | 20 | 20 | 2020-05-20 | Carol and Garry | Docs uploaded to CSC Portal
1.3 | Appoint Taskforce Coordinator | 10 | 10 | 2020-05-20 | Carol and Garry | Docs uploaded to CSC Portal
Priority
2.1 | Develop government oprations GHG emissions inventory | 16 | 16 | 2022-02-21 | Gary and Aaron | Hamilton students assist
7.1 | Conduct Vulnerability Assessment | 4 | 16 | 2021-12-31 | Aaron | report being finalized
9.1 | Climate Change Education and Engagement | 4 | 8 | 2022-06-30 | Alma | Alma Prepared Initial Draft, Subcommittee to work on
2.6 | Develop Community Climate Action Plan | 16 | 16 | 2023-06-30 | Alma and Aaron | to begin Spring, 2022 with assistance and input from Ham students and community?
Others
3.32 | Complete energy benchmarking for govt bldgs | 2 | 4 | 2021-01-31 | Gary & Aaron | CEC action, docs uploaded. Town should publish annually on website for 4 points.
3.15 | Install LED streetlights | 5 | 10 | 2020-07-19 | Garry | CEC action, docs uploaded
3 | Energy Code Enforcemet Training | 5 | 5 | 2020-07-19 | Gary | CEC action, docs uploaded
6.3 | Adopt Unified Solar Permit | 5 | 5 | 2020-07-19 | Gary | CEC action, docs uploaded
3.2 | Interior Lighting Upgrades | 1 | 5 | 2021-01-31 | Gary & Carol | completed and docs uploaded to CSC
10.3 | Partership with Other Entities | 3 | 3 | 2021-01-31 | Carol | completed and info uploaded to CSC
1.5 | National/Regional Climate Program | 3 | 3 | 2021-01-31 | Carol | completed and info uploaded to CSC
9.4 | Develop and maintain website on CSC | 3 | 3 | 2020-09-20 | Alan & Alma | completed and info uploaded to CSC
8 | Community Campaign (Heatsmart Clean Heating) | 3 | 3 | 2022-04-27 | Steve O | completed and info uploaded to CSC
9 | Climate related Public Event (EV at Car Show) | 3 | 3 | 2022-06-13 | Sally C | completed and info uploaded to CSC
6.9 | Adopt Complete Streets Policy- Priority Action | 0 | 0 | 2021-05-21 | Kathy and Steve | Resolution passed, but need plan on how to achieve for CSC points
5.11 | Yard Waste Collection Program | 2 | 22 | 2021-11-21 | Liseli & Mona | completed and info uploaded to CSC
9.4 | Social Media to inform public about progress | 3 | 3 | 2021-12-31 | Alan & Alma
10.1 | Report Progress Annually | 4 | 4 | 2021-12-31 | All | progress rpt generally describes progress on climate action plan or other action oriented plan on climate initiative
| Total | 112 | 159
Other Actions to Consider
7.15 | Natl Flood Insur Prog Comm Rating System | 3 | 9 |  | Aaron and Steve | May discuss at Meeting on Flooding
| Total with additional considered actions | 115 | 168
Note: 3 Prioirity Actions and 120 points required to achieve bronze
2022-08-09